## Sheet1
Tasks Listed by their priority | Affiliated Engineers | Time Budget | Priority | Evaluation
Merge NSA branch into the Beta branch | Collin,Josh | 1 week 4 days | 1
facebook integration(profile picture) | Thomas,Josh | 2 weeks | 2
Allow users to add multiple schedules | Josh,Abe,Collin | 3 weeks | 3
Add news feed | Eric | 2 week2 | 4
Allow users to have non-class events in their schedule | Naphtali | 2 weeks | 5
Polish the UI in terms of color and usability | Abe | 3 weeks | 6
Recreate the settings fragment | Naphtali | 1 week 2 days | 7
Allow users to rate classes by fun,grade earned,usefullness | Eric | 2 week | 8
Support academic holidays in the schedule | Collin | 1 week 3 days | 9
Add food venue times | Abe | 1 week 3 days | 10
Add a feed of school events | Eric | 1 week 3 days | 11
support gesture control | Abe,Collin | 1 week 2 days | 12